## Work Log
Date | Number of Hours | Description | Remarks
2026-01-09 | 3 | Initial class of the CSIS 4495 | Inital idea of the research project ofthe HRIS platform extension was extended to Prof. Priya and she gave the idea of Work Safety Dashboard
2026-01-10 | 1 | Research done on the worksafe practices and the availability of the similar dashboards
2026-01-12 | 0.3 | Spoke to the HR of the Fairmon Waterfront to get the data
2026-01-15 | 0.5 | searched about the technology that I have to use and created the Git hub Repo and sent the colloboration request to Prof. Priya
2026-01-16 | 3 | Project discussion with Prof. Priya and Finalizing the scope
2026-01-20 | 2 | Project Proposal draft
2026-01-21 | 1 | Project Proposal draft
2026-01-22 | 0.5 | Project Proposal draft
2026-01-24 | 2 | Project Proposal draft
2026-01-25 | 2 | Finalizing the research project
2026-01-30 | 2 | Mandatory consultation with supervisor | Discussed project direction and received guidance to obtain operational requirements from Fairmont Waterfront
2026-02-01 | 1 | Development environment setup | Configured local development environment and required tools for system development
2026-02-02 | 2 | Meeting with Fairmont Waterfront HR department | Collected operational insights from HR to prioritise system features, as advised by the supervisor
2026-02-03 | 2 | Developed Backend (Application Layer) using Node.js and Express. | Installed dependencies and wrote index.js for DB connectivity.
2026-02-04 | 1 | Dataset and industry research | Conducted in-depth research on relevant datasets and reviewed comparable workplace safety systems
2026-02-05 | 2 | Dashboard feature research | Analysed and shortlisted core features required for the SafeSight dashboard
2026-02-06 | 2 | Dataset cleaning and SQL import | Cleaned selected datasets and prepared them for import into the SQL database
2026-02-07 | 1 | Integrated React.js Frontend (Presentation Layer). | Scaffolded the React app inside the FrontEnd directory.
2026-02-07 | 0.5 | Verified Full-Stack connection and committed changes to GitHub. Confirmed "Connected to SafeSight MySQL Database" in terminal.
2026-02-08 | 1 | SafeSight data preparation (Jupyter Notebook) | Developed and documented data preparation steps using a Jupyter Notebook
2026-02-09 | 3 | Progress Report 1 finalisation | Compiled, reviewed, and finalised Progress Report 1 for submission
2026-02-09 | 3 | Phase 2 headstart with bridging presentation layer and the data layer
2026-02-10 | 2 | Database Schema Optimization | Refined MySQL tables to ensure data integrity for incident severity mapping.
2026-02-11 | 1.5 | API Endpoint Development | Created Node.js routes to fetch total incident counts and hospitalization data.
2026-02-12 | 2 | Frontend Dashboard Integration | Integrated Recharts library into React to display the Incident Velocity Trend.
2026-02-13 | 1.5 | Component Styling | Designed the "SafeSight Intelligence Analytics" header and high-level stat cards.
2026-02-14 | 2.5 | Data Mapping: Fairmont Waterfront | Successfully mapped 391 historical records to the dashboard visualization layer.
2026-02-15 | 2 | Severity Distribution Logic | Programmed the pie chart logic to categorize "Critical" (83) and "High" (297) risks.
2026-02-16 | 2 | Departmental Risk Profiling | Developed the bar chart component to identify Housekeeping as the top risk area.
2026-02-17 | 1.5 | Research Access Configuration | Implemented "HR" research access level labels and restricted views in the UI.
2026-02-18 | 2 | Midterm Presentation Planning | Outlined the 10-minute presentation script for the full-stack system.
2026-02-19 | 1 | Navigation & UI Logic | Finalized the top navigation bar links for Dashboard, Analytics, and WorkSafeBC.
2026-02-20 | 2.5 | Analytics Calculations | Verified the 97.1% risk probability metric against the 380 identified critical risks.
2026-02-21 | 2 | Script Refinement | Developed detailed speaking notes for role-based features and technical architecture.
2026-02-22 | 2 | Roadmap & Worklog Finalization | Documented future AI implementation plans and finalized the Phase 2 development log.
2026-02-23 | 2 | AI Service Setup | Initialized the AI_Service directory, configured a Python Virtual Environment (venv) to isolate Machine Learning dependencies.
2026-02-24 | 1 | ML Model Training | Developed the Random Forest Classifier script using Scikit-Learn; implemented LabelEncoder to process categorical hotel data.
2026-02-25 | 1 | Flask API Development | Created a Flask web server to host the ML model; established the /ai/predict-risk endpoint for real-time inference.
2026-02-26 | 1 | Backend Integration | Modified the Node.js server.js to act as an API Gateway; integrated Axios to fetch data from the Python service (Port 5001).
2026-02-27 | 3 | Midterm Check-in | Advised to add a chatbot and a export version of worksafebc
2026-02-28 | 1 | CORS & Networking | Resolved Cross-Origin Resource Sharing (CORS) conflicts between the three running services (Ports 3000, 5000, and 5001).
2026-03-01 | 2 | Frontend UI Dev | Developed the Prediction.js React component; mapped AI "Risk Probabilities" to a visual dashboard for HR personnel.
2026-03-02 | 2 | Progress Report 2 Preparation

## AI
AI Tool Name | Version / Account Type | Specific Feature Used | Prompt Used (Summary) | Value Addition (Student Contribution)
ChatGPT | GPT-5.2 / Free | Idea generation & academic structuring | “Suggest HRIS add-ons related to workplace safety systems” | Evaluated relevance, selected only safety-focused HRIS features, and adapted them to Fairmont Waterfront context
ChatGPT | GPT-5.2 / Free | Comparative analysis | “List available work and safety systems used in hospitality” | Analysed limitations of existing systems and identified gaps SafeSight addresses
ChatGPT | GPT-5.2 / Free | Academic writing support | “Provide a format for a literature review” | Reorganised structure to meet postgraduate marking rubric and project scope
ChatGPT | GPT-5.2 / Free | Analytical framework explanation | “Explain types of gap analysis for information systems” | Selected operational and compliance gap analysis suitable for WorkSafeBC context
ChatGPT | GPT-5.2 / Free | Research methodology structuring | “Provide format of a research design” | Tailored design to technical system development rather than theoretical research
ChatGPT | GPT-5.2 / Free | Methodology guidance | “How to form a research design for technical development research” | Aligned SDLC phases with academic research expectations
ChatGPT | GPT-5.2 / Free | Research methods suggestion | “Data collection methods for technical research projects” | Selected simulated datasets and system-generated data relevant to safety analytics
ChatGPT | GPT-5.2 / Free | Research validation strategy | “Explain triangulation strategies in applied research” | Applied triangulation using system output, predictive results, and usability feedback
ChatGPT | GPT-5.2 / Free | Technology recommendation | “Identify technology stack for a full-stack predictive dashboard” | Finalised stack based on feasibility, course scope, and personal skill level
ChatGPT | GPT-5.2 / Free | Code generation | “Generate Mermaid code for Kanban timeline” | Validated task logic, adjusted timelines, and aligned with Gantt and PERT plans
ChatGPT | GPT-5.2 / Free | System design explanation | “Describe three-tier system architecture for a safety system” | Adapted architecture specifically for HR, manager, and reporting portals
ChatGPT | GPT-5.2 / Free | Formal document drafting | “Draft a project contract for academic proposal” | Simplified language, aligned with course outline, and customised for instructor
M365 Copilot | GPT‑5 chat model / Free | Logo creation | "create a logo for work safety dashboard name: SafeSight"
ChatGPT | GPT-5.2 / Free | Database design guidance | “Suggest database structure for a workplace safety analytics system” | Reviewed proposed schema, normalised tables, and selected entities relevant to hospitality safety incidents
ChatGPT | GPT-5.2 / Free | Data modelling explanation | “Explain relational vs analytical database models” | Chose relational model for transactional safety data and justified design choice in report
ChatGPT | GPT-5.2 / Free | Dataset cleaning guidance | “How to clean and prepare incident datasets for predictive analysis” | Applied only applicable cleaning steps and excluded unrealistic transformations for simulated data
ChatGPT | GPT-5.2 / Free | Data validation rules | “What validation checks are required for safety datasets” | Defined validation rules aligned with workplace incident reporting standards
ChatGPT | GPT-5.2 / Free | Front-end architecture explanation | “Explain front-end architecture for a data dashboard” | Selected dashboard-based UI approach suitable for managers and HR users
ChatGPT | GPT-5.2 / Free | Back-end design support | “Describe back-end services for analytics systems” | Mapped suggested services to a simplified API structure appropriate for course scope
ChatGPT | GPT-5.2 / Free | API design guidance | “Design REST API endpoints for a safety reporting system” | Filtered endpoints to core MVP features and documented them at a conceptual level
ChatGPT | GPT-5.2 / Free | Environment setup guidance | “Development environment setup for full-stack analytics project” | Selected tools and configurations compatible with local machine and institutional constraints
ChatGPT | GPT-5.2 / Free | Deployment awareness | “Common deployment considerations for academic system projects” | Identified constraints and documented limitations rather than attempting premature deployment
ChatGPT | GPT-5.2 / Free | Progress report structuring | “Provide a format for Progress Report 1 for a system development project” | Selected only sections required by course guidelines and adapted structure to reflect SafeSight’s early development stage
ChatGPT | GPT-5.2 / Free | Milestone planning | “Identify suitable milestones for Phase 1 of a predictive system project” | Refined milestones to align with completed research activities and realistic academic timelines
ChatGPT | GPT-5.2 / Free | Scope clarification | “Explain how to define project scope for an applied IT research project” | Clarified system boundaries and excluded advanced features not feasible within course duration
ChatGPT | GPT-5.2 / Free | Requirement prioritisation | “How to prioritise functional requirements for an MVP system” | Evaluated suggested requirements and selected core safety analytics features for initial implementation
ChatGPT | GPT-5.2 / Free | Risk and issue identification | “Common early-stage risks in system development projects” | Identified relevant risks and documented mitigation strategies applicable to SafeSight development
ChatGPT | GPT-5.2 / Free | Academic reflection support | “How to write reflective progress for an IT project” | Rewrote content in own words, ensuring critical reflection rather than descriptive reporting
ChatGPT | GPT-5.2 / Free | Alignment check | “How to align progress reports with original project proposal” | Cross-checked progress against proposal objectives and adjusted report to maintain consistency
Gemini | Paid | Technical Troubleshooting | "Troubleshooting Node" | Resolved backend connectivity issues and port 5000 configuration.
Gemini | Paid | Full-Stack Integration | "Bridging the layers" | Successfully linked MySQL queries to React frontend components.
Gemini | Paid | Data Visualization | "Dashboard stats and Recharts" | Developed logic for Severity Distribution and Velocity Trend charts.
Gemini | Paid | UX Design Analysis | "AIDA framework for Dashboard" | Applied information hierarchy to prioritize Critical Risks (380) and Hospitalization (345) stats.
Gemini | Paid | Business Logic | "Departmental Risk Profile" | Identified Housekeeping as the primary risk area with 82+ incidents.
Gemini | Paid | Content Creation | "10-minute presentation script" | Structured a professional narrative for the solo midterm presentation.
Gemini | 3 Flash / Free Tier | Multi-service Integration | "How do I connect a Python Flask ML service to a Node.js Express backend?" | Architectural Design: Defined the three-port strategy (3000, 5000, 5001) and integrated the bridge logic.
ChatGPT | GPT-4o (Free) | Initial Code Logic | "Write a basic Random Forest Classifier for workplace safety incidents." | Algorithm Selection: Evaluated the generated script against hotel-specific data requirements to ensure model accuracy.
Claude | 3.5 Sonnet (Free) | Technical Documentation | "Summarize my recent technical tasks into professional report language." | Communication: Refined the raw technical notes into the professional "Summary of Work" and "Technical Details" used in this report.
Gemini | 3 Flash / Free Tier | Troubleshooting | "Resolve CORS error between React and Flask using the flask-cors library." | System Orchestration: Manually configured middleware in both services and verified the secure handshake across the local network.

## Prompts
AI Tool name | Version, Account type | Specific feature for which the AI tool was used | Prompt | Value Addition What value did you add over and above what AI did for you?
HRIS Add ons
Available Work and Safety Systems
Format of a literature review
Types of Gap Analysis
Format of a research design
How to form a research design for a technical development research
Data collection methods for a Technical research
Triangulation strategy
Technology Stack Identification
Code for timeline to draw the KANBAN chart
System Architecture
Project contract