## WBS Project (hidden)
WORK BREAKDOWN STRUCTURE
PROJECT TITLE |  |  | START DATE
Pet Adoption Website
PROJECT MANAGER |  |  | END DATE |  | PROJECT DURATION
ID | TASK | DESCRIPTION | START DATE | END DATE | DURATION | COMMENTS
1 | Phase 1 - Planning
1.1 | Define Project Scope & Requirements | Document project goals, features, and requirements for the pet adoption platform.
1.2 | Create Project Timeline | Develop schedule with milestones and deadlines for project completion.
1.3 | Allocate Resources & Team Roles | Assign team members to roles and distribute project resources.
2 | Phase 2 - Design
2.1 | Research & Analysis | Study existing pet adoption platforms and identify user needs.
2.2 | Develop Wireframes & Prototypes | Create basic layout designs and clickable prototypes.
2.3 | Design Website Layout & UI | Design user interface elements and page layouts.
2.4 | Create Branding Elements | Design logo, select colors, and establish visual identity.
3 | Phase 3 - Development
3.1 | Set Up Development Environment | Configure development tools, servers, and databases.
3.2 | Backend Development | Build server-side functionality and database structure
3.3 | Frontend Development | Create user interface and implement responsive design.
4 | Phase 4 - Testing and Demo
4.1 | Functional Testing | Test all platform features and functionality.
4.2 | User Acceptance Test UAT | Conduct testing with sample users to validate platform.
4.3 | Bug Fixing & Re-testing | Fix identified issues and perform regression testing
4.4 | Demonstration | Present completed platform to stakeholders.

## WBS Phase 3 (hidden)
WORK BREAKDOWN STRUCTURE
PHASE 3 |  |  | START DATE
Development
LEAD |  |  | END DATE |  | PHASE DURATION
ID | TASK | DESCRIPTION | START DATE | END DATE | DURATION | COMMENTS
3.1 | Account Management
3.1.1 | Edit Profile Name | Allow users to update their display name on their account.
3.1.2 | Edit Picture | Enable users to upload and change their profile picture.
3.1.3 | Change Password | Provide functionality for users to update their account password securely.
3.2 | Pet Browsing
3.2.1 | Browsing | Display a grid/list view of available pets for adoption.
3.2.2 | Filtering and Searching | Enable users to search pets by criteria like breed, location.
3.2.3 | Accessing Pet Details | View information about individual pets including photos and descriptions.
3.3 | Pet Management
3.3.1 | Uploading Pet | Allow staff to add new pets to the adoption platform
3.3.2 | Deleting Pet | Enable removal of pet listings once they're adopted or no longer available.
3.3.3 | Editing Pet Information | Update pet details, photos, and adoption status
3.4 | Authentication
3.4.1 | Login | Securely access user accounts with email/username and password.
3.4.2 | Registration | Create new user accounts with basic profile information.

## WBS Phase 3v2 (hidden)
WORK BREAKDOWN STRUCTURE
PHASE 3 |  |  | START DATE
Development
LEAD |  |  | END DATE |  | PHASE DURATION
ID | TASK | DESCRIPTION | START DATE | END DATE | DURATION | COMMENTS
3.1 | Account Management
3.1.1 | Edit Profile Name | Allow users to update their display name on their account.
3.1.2 | Edit Picture | Enable users to upload and change their profile picture.
3.1.3 | Change Password | Provide functionality for users to update their account password securely.
3.2 | Pet Browsing
3.2.1 | Browsing | Display a grid/list view of available pets for adoption.
3.2.2 | Filtering and Searching | Enable users to search pets by criteria like breed, location.
3.2.3 | Accessing Pet Details | View information about individual pets including photos and descriptions.
3.3 | Pet Management
3.3.1 | Uploading Pet | Allow staff to add new pets to the adoption platform
3.3.2 | Deleting Pet | Enable removal of pet listings once they're adopted or no longer available.
3.3.3 | Editing Pet Information | Update pet details, photos, and adoption status
3.4 | Authentication
3.4.1 | Login | Securely access user accounts with email/username and password.
3.4.2 | Registration | Create new user accounts with basic profile information.

## Gantt Chart
GANTT CHART
PROJECT TITLE |  | START DATE |  | DISPLAY WEEK
SafeSight |  | 2026-01-20 |  | 1
PROJECT MANAGER |  | END DATE |  | PROJECT DURATION
Sandali Silva |  | 2025-04-10 |  | 3 Months
[6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30
 | time axis 2026-01-19 to 2026-04-05
| TASK |  | START DATE | DAYS | END DATE | time axis 2026-01-19 to 2026-04-05
1 | Domain Analysis & Requirements |  | 2026-01-20 |  | 2026-01-27
1.1 | Define Project Scope & Requirements |  | 2026-01-20 | 5 | 2026-01-24
1.2 | Create Project Timeline |  | 2026-01-25 | 1 | 2026-01-25
1.3 | Allocate Resources |  | 2026-01-25 | 1 | 2026-01-27
2 | System Design & Development |  | 2026-01-27 |  | 2026-03-01
2.1 | Research & Analysis |  | 2026-01-27 | 7 | 2026-02-02
2.2 | Develop Wireframes & Prototypes |  | 2026-02-03 | 14 | 2026-02-16
2.3 | Design Website Layout & UI |  | 2026-02-16 | 10 | 2026-02-27
2.4 | Create Branding Elements |  | 2026-02-28 | 2 | 2026-03-01
3 | Development |  | 2026-03-07 |  | 2026-04-03
3.1 | Frontend Development |  | 2026-03-01 | 7 | 2026-03-07
3.2 | Backend API Development |  | 2026-03-07 | 4 | 2026-03-10
3.3 | Registration |  | 2026-03-10 | 5 | 2026-03-14
3.4 | Authentication & Role Management |  | 2026-03-14 | 2 | 2026-03-16
3.5 | WorkSafeBC Report Automation |  | 2026-03-12 | 2 | 2026-03-13
3.6 | Data Collection & Cleaning |  | 2026-03-13 | 3 | 2026-03-15
3.7 | Feature Engineering & Data Prep |  | 2026-03-16 | 4 | 2026-03-19
3.8 | Predictive Model Development |  | 2026-03-19 | 4 | 2026-03-22
3.9 | Model Training & Validation |  | 2026-03-20 | 5 | 2026-03-24
3.1 | Prediction API Integration |  | 2026-03-24 | 7 | 2026-03-30
3.11 | Dashboard |  | 2026-03-25 | 7 | 2026-03-31
3.12 | Visualizations |  | 2026-03-26 | 3 | 2026-03-28
3.13 | Account Management |  | 2026-03-26 | 2 | 2026-03-27
3.14 | Edit Profile |  | 2026-03-27 | 7 | 2026-04-02
3.15 | HR departmental view |  | 2026-03-28 | 7 | 2026-04-03
3.16 | Report Generation |  | 2026-03-29 | 2 | 2026-03-30
4 | Testing and Demo |  | 2026-03-30 |  | 2026-04-08
4.1 | Functional Testing |  | 2026-03-30 | 2 | 2026-03-31
4.2 | User Acceptance Test UAT |  | 2026-03-31 | 1 | 2026-03-31
4.3 | Bug Fixing & Re-testing |  | 2026-04-01 | 3 | 2026-04-03
4.4 | Demonstration & Submission |  | 2026-04-08 | 1 | 2026-04-08

## Scheduling Critical Path (hidden)
SCHEDULING TASK
TASK | 3.2 |  | START DATE
Pet Management
LEAD |  |  | END DATE |  | TASK DURATION
15
ID | ACTIVITY | PREDECESSOR | DURATION | RESPON | ES | EF | LS | LF | SLACK | CRITICAL | ES |  | EF
Activity Description
1 | Develop Pet model in back-end |  | 1 | Ian | 0 | 1 | 0 | 1 | 0 | Yes
2 | Develop POST endpoint for pet | 1 | 2 | Ian | 1 | 3 | 2 | 4 | 1 | No | ID | R | D
3 | Develop DELETE endpoint for pet | 1 | 2 | Ian | 1 | 3 | 2 | 4 | 1 | No | LS |  | LF
4 | Develop PUT endpoint for pet | 1 | 2 | Ian | 1 | 3 | 2 | 4 | 1 | No
5 | Develop GET endpoint for pet | 1 | 3 | Ian | 1 | 4 | 1 | 4 | 0 | Yes | ES | Earliest Start
6 | Handle image saving and deleting | 2, 3, 4, 5 | 1 | Ian | 4 | 5 | 4 | 5 | 0 | Yes | EF | Earliest Finish
7 | Testing backend | 6 | 2 | Tommy | 5 | 7 | 5 | 7 | 0 | Yes | LS | Latest Start
8 | Wireframe for pet management layout | 6 | 1 | Upul | 5 | 6 | 6 | 7 | 1 | No | LF | Latest Finish
9 | Develop front-end interfaces and forms | 7, 8 | 4 | Ian | 7 | 11 | 7 | 11 | 0 | Yes | ID | Activity Number
10 | Integrating front-end with back-end | 9 | 2 | Ian | 11 | 13 | 11 | 13 | 0 | Yes | D | Estimated Duration
11 | Testing integration | 10 | 2 | Tommy | 13 | 15 | 13 | 15 | 0 | Yes | R | Responsible Person

## Sheet1 (hidden)
SCHEDULING TASK
TASK | 3.2 |  | START DATE
Pet Management
LEAD |  |  | END DATE |  | TASK DURATION
15
ID | ACTIVITY | PREDECESSOR | DURATION | RESPON | ES | EF | LS | LF | SLACK | CRITICAL
1 | Develop Pet model in back-end |  | 1 | Ian | 0 | 1 | 0 | 1 | 0 | Yes
2 | Develop POST endpoint for pet | 1 | 2 | Ian | 1 | 3 | 2 | 4 | 1 | No
3 | Develop DELETE endpoint for pet | 1 | 2 | Ian | 1 | 3 | 2 | 4 | 1 | No
4 | Develop PUT endpoint for pet | 1 | 2 | Ian | 1 | 3 | 2 | 4 | 1 | No
5 | Develop GET endpoint for pet | 1 | 3 | Ian | 1 | 4 | 1 | 4 | 0 | Yes
6 | Handle image saving and deleting | 2, 3, 4, 5 | 1 | Ian | 4 | 5 | 4 | 5 | 0 | Yes
7 | Testing backend | 6 | 2 | Tommy | 5 | 7 | 5 | 7 | 0 | Yes
8 | Wireframe for pet management layout | 6 | 1 | Upul | 5 | 6 | 6 | 7 | 1 | No
9 | Develop front-end interfaces and forms | 7, 8 | 4 | Ian | 7 | 11 | 7 | 11 | 0 | Yes
10 | Integrating front-end with back-end | 9 | 2 | Ian | 11 | 13 | 11 | 13 | 0 | Yes
11 | Testing integration | 10 | 2 | Tommy | 13 | 15 | 13 | 15 | 0 | Yes

## Network Diagram (hidden)
SCHEDULE NETWORK DIAGRAM
0 |  | 1 | 1 |  | 3
Develop Pet model in back-end |  |  | Develop POST endpoint for pet
1 | Ian | 1 | 2 | Ian | 2
0 |  | 1 | 2 |  | 4
1 |  | 3 | 1 |  | 3
Develop DELETE endpoint for pet |  |  | Develop PUT endpoint for pet
3 | Ian | 2 | 4 | Ian | 2
2 |  | 4 | 2 |  | 4
1 |  | 4 | 4 |  | 5
Develop GET endpoint for pet |  |  | Handle image saving and deleting
5 | Ian | 3 | 6 | Ian | 1
1 |  | 4 | 4 |  | 5
5 |  | 7 | 5 |  | 6
Testing backend |  |  | Wireframe for pet management layout
7 | Tommy | 2 | 8 | Upul | 1
5 |  | 7 | 6 |  | 7
7 |  | 11 | 11 |  | 13
Develop front-end interfaces and forms |  |  | Integrating front-end with back-end
9 | Ian | 4 | 10 | Ian | 2
7 |  | 11 | 11 |  | 13
13 |  | 15
Testing integration
11 | Tommy | 2
13 |  | 15

## Backlog and Sprints (hidden)
Sprint Breakdown (Focused Themes)
| Sprint | Theme | User Story | Priority | Status | Components
1 | Sprint 1 | Pet Management | As a pet owner, I want to add new pets to the system | High | Done | PetController, ManagementDashboard
2 | Sprint 1 | Pet Management | As a pet owner, I want to edit my pet listings | High | Done | PetController, ManagementDashboard
3 | Sprint 1 | Pet Management | As a pet owner, I want to delete my pet listings | High | Done | PetController, ManagementDashboard
4 | Sprint 1 |  |  | High | Done | PetController, ManagementDashboard
5 | Sprint 1 | Pet Management | As a user, I want to view all pets up for adoption in a single web page. | Medium | Done | PetController, SimplePetDTO
6 | Sprint 2 | Authentication | As a user, I want to create an account | High | Done | UserController, UserRepository
7 | Sprint 2 | Authentication | As a user, I want to login to my account | High | Done | LoginController, AuthenticationService
8 | Sprint 2 | Authentication | As a system, I want to encrypt passwords | High | Done | PasswordEncrypter
9 | Sprint 3 | Enhancements | As a user, I want to filter pets by type/size/location | Medium | To Do | PetRepository
10 | Sprint 3 | Enhancements | As a user, I want to view detailed pet profiles to learn more about potential adoptees. Acceptance Criteria: | Medium | To Do | DetailedPetDTO
11 | Sprint 3 |  | As a user, I want to view and give ratings for the shelters based on the experience of adopting. | Medium | To Do | Frontend components
As a user, I want to inquire about pets I'm interested in adopting.
|  | Theme | User Story | Sprint | Priority | Status
|  | Authentication | US1 - Registration | 1 | High | Done
|  | Authentication | US2 - Login | 1 | High | Done
|  | Pet Management | US3 - Uploading Pet | 1 | High | Done
|  | Pet Management | US4 - Deleting Pet | 2 | High | Done
|  | Pet Management | US5 - Editing Pet | 2 | High | Done
|  | Pet Browsing | US6 - Guest Browsing | 2 | High | Done
|  | Pet Browsing | US7 - Filtering and Searching | 3 | Medium | To Do
|  | Pet Browsing | US8 - Pet Inquiries | 3 | Medium | To Do
|  | Account Management | US10 - Edit Profile Name and Details | 4 | Medium | To Do
|  | Account Management | US11 - Change Password | 4 | Low | To Do
|  | Account Management | US12 - Edit Profile Picture | 4 | Low | To Do
|  | Pet Browsing | US9 - Shelter Rating System | 4 | Low | To Do

## Business Case Financials (hidden)
Year 2
Month Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Year 2
Active Registrations - Opening | 0 | 13.3333 | 26.6667 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80
Net Addition | 13.3333 | 13.3333 | 13.3333 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Active Registrations - Closing | 13.3333 | 26.6667 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 85
Subscription Rate | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39
Revenue | 260 | 780 | 1300 | 1657.5 | 1852.5 | 2047.5 | 2242.5 | 2437.5 | 2632.5 | 2827.5 | 3022.5 | 3217.5 | 24277.5
Website Hosting and Maintenance Cost | -300 | -309 | -318.27 | -327.8181 | -337.6526 | -347.7822 | -358.2157 | -368.9622 | -380.031 | -391.432 | -403.1749 | -415.2702 | -4257.6089
Sales and Marketing Cost | 13.3333: -1000; 26.6667: -500; 40: -500; 85: -2000
Profit | -1040 | -29 | 481.73 | 1329.6819 | 1514.8474 | 1699.7178 | 1884.2843 | 2068.5378 | 2252.469 | 2436.068 | 2619.3251 | 2802.2298 | 18019.8911
Assumptions
Running cost of the Website per month | 13.3333: 300
Average net addition for 1-3 months | 13.3333: 13
Average net addition for 4 month onwards | 13.3333: 5
Sales and Marketing Investment | 13.3333: 2000